## Sprint Overview
MARKA AI - Sprint Overview
Sprint | Name | Duration | Start Date | End Date | Focus | Status
Sprint 1 | Infrastructure & Foundation | 2 weeks | Week 1 | Week 2 | Repository, Docker, Database Setup | Pending
Sprint 2 | Core AI Layer | 3 weeks | Week 3 | Week 5 | Agents, LLM Service, Config | Pending
Sprint 3 | API Layer | 2 weeks | Week 6 | Week 7 | FastAPI Endpoints, Auth, Middleware | Pending
Sprint 4 | RAG System | 2 weeks | Week 8 | Week 9 | MongoDB, Qdrant, Embeddings | Pending
Sprint 5 | Frontend - Telegram Bot | 2 weeks | Week 10 | Week 11 | Bot Commands, Handlers | Pending
Sprint 6 | Frontend - Web UI | 2 weeks | Week 12 | Week 13 | React Pages, Forms | Pending
Sprint 7 | Integration & Testing | 2 weeks | Week 14 | Week 15 | CI/CD, Testing, Deployment | Pending

## Task Breakdown
MARKA AI - Detailed Task Breakdown
Task ID | Sprint | Task Name | Description | Owner | Priority | Dependencies | Est. Hours | Status
T001 | Sprint 1 | Repository Setup | Create monorepo structure with ai/, bot/, web/ directories | Ahmed | High | - | 4 | Pending
T002 | Sprint 1 | Docker Compose Configuration | Set up docker-compose.yml with all services | Ahmed | High | T001 | 6 | Pending
T003 | Sprint 1 | MongoDB Container Setup | Configure MongoDB with health checks and volumes | Yomna | High | T002 | 3 | Pending
T004 | Sprint 1 | Qdrant Container Setup | Configure Qdrant with health checks and volumes | Yomna | High | T002 | 3 | Pending
T005 | Sprint 1 | FastAPI Base Structure | Create main.py, config.py, basic folder structure | Ahmed | High | T001 | 4 | Pending
T006 | Sprint 1 | Environment Configuration | Create .env.example with all required variables | Ahmed | High | T001 | 2 | Pending
T007 | Sprint 1 | Pyproject.toml Setup | Configure uv package manager dependencies | Ahmed | Medium | T001 | 2 | Pending
T008 | Sprint 1 | GitHub Branch Strategy | Set up main, develop, feature branches | Ahmed | Medium | T001 | 2 | Pending
T009 | Sprint 2 | LiteLLM Service Integration | Create llm_service.py with LiteLLM wrapper | Ahmed | High | T005 | 8 | Pending
T010 | Sprint 2 | LLM Provider Configuration | Configure Gemini, Mistral, Groq fallback models | Ahmed | High | T009 | 4 | Pending
T011 | Sprint 2 | Orchestrator Agent | Build orchestrator.py with if/else routing | Ahmed | High | T009 | 8 | Pending
T012 | Sprint 2 | RAG Agent | Build rag.py for brand voice retrieval | Yomna | High | T009 | 8 | Pending
T013 | Sprint 2 | Content Agent | Build content.py for Arabic marketing copy | Ahmed | High | T009 | 10 | Pending
T014 | Sprint 2 | Chatbot Agent | Build chatbot.py for intent parsing | Yomna | High | T009 | 8 | Pending
T015 | Sprint 2 | Agent Prompts Design | Design Egyptian dialect prompts for all agents | Ahmed | High | T011, T012, T013, T014 | 6 | Pending
T016 | Sprint 2 | Rate Limiting Implementation | Implement in-memory rate limiter middleware | Shared | Medium | T005 | 4 | Pending
T017 | Sprint 3 | Health Check Endpoint | Create /health GET endpoint | Shared | High | T005 | 2 | Pending
T018 | Sprint 3 | API Token Authentication | Implement X-API-Token middleware | Ahmed | High | T005 | 4 | Pending
T019 | Sprint 3 | Chat Endpoint | Create /api/v1/chat POST endpoint | Yomna | High | T014 | 6 | Pending
T020 | Sprint 3 | Generate Endpoint | Create /api/v1/generate POST endpoint | Ahmed | High | T013 | 6 | Pending
T021 | Sprint 3 | Publish Endpoint | Create /api/v1/publish POST endpoint | Ahmed | High | T020 | 6 | Pending
T022 | Sprint 3 | RAG Search Endpoint | Create /api/v1/rag/search POST endpoint | Yomna | High | T012 | 6 | Pending
T023 | Sprint 3 | Brand Management Endpoints | Create /api/v1/brand GET/POST endpoints | Yomna | High | T012 | 4 | Pending
T024 | Sprint 3 | Error Handling Middleware | Create errors.py with standardized error responses | Shared | Medium | T005 | 3 | Pending
T025 | Sprint 3 | Pydantic Schemas | Create request/response schemas for all endpoints | Shared | High | T019, T020, T021, T022, T023 | 4 | Pending
T026 | Sprint 3 | Apidog API Documentation | Document all endpoints in Apidog | Both | Medium | T017-T025 | 4 | Pending
T027 | Sprint 4 | MongoDB Service | Create mongodb_service.py with connection handling | Shared | High | T003 | 6 | Pending
T028 | Sprint 4 | Qdrant Service | Create qdrant_service.py with deterministic IDs | Yomna | High | T004 | 8 | Pending
T029 | Sprint 4 | Embedding Generation | Implement text-embedding-004 integration (768 dims) | Yomna | High | T010, T028 | 6 | Pending
T030 | Sprint 4 | Vector Storage Logic | Implement point creation and upsert to Qdrant | Yomna | High | T028, T029 | 6 | Pending
T031 | Sprint 4 | Brand Memory Model | Create brand_memory.py Pydantic model | Yomna | High | T027 | 4 | Pending
T032 | Sprint 4 | Job History Model | Create job_history.py Pydantic model | Ahmed | High | T027 | 4 | Pending
T033 | Sprint 4 | Job State Management | Create job_state.py with in-memory state + cleanup | Ahmed | High | T027 | 6 | Pending
T034 | Sprint 4 | Semantic Search Implementation | Implement similarity search with Qdrant | Yomna | High | T028, T030 | 8 | Pending
T035 | Sprint 5 | Bot Main Setup | Create bot/main.py with polling and startup | Ahmed | High | T005 | 4 | Pending
T036 | Sprint 5 | wait_for_api() Health Check | Implement startup retry loop for FastAPI readiness | Ahmed | High | T035 | 3 | Pending
T037 | Sprint 5 | /start Command Handler | Implement welcome + product description prompt | Ahmed | High | T035 | 4 | Pending
T038 | Sprint 5 | /new Command Handler | Implement new campaign creation flow | Ahmed | High | T037 | 6 | Pending
T039 | Sprint 5 | /generate Command Handler | Implement caption generation trigger | Ahmed | High | T038, T020 | 6 | Pending
T040 | Sprint 5 | /publish Command Handler | Implement selected caption publishing | Ahmed | High | T039, T021 | 6 | Pending
T041 | Sprint 5 | /help Command Handler | Implement available commands display | Ahmed | Medium | T035 | 2 | Pending
T042 | Sprint 5 | Bot Dockerfile | Create Dockerfile for Telegram bot container | Ahmed | High | T035 | 2 | Pending
T043 | Sprint 6 | React Project Setup | Initialize React project with TypeScript | Ahmed | High | T001 | 4 | Pending
T044 | Sprint 6 | API Client | Create client.ts with X-API-Token auth | Ahmed | High | T043, T018 | 4 | Pending
T045 | Sprint 6 | Landing Page | Create landing + quick generate form | Ahmed | Medium | T043 | 6 | Pending
T046 | Sprint 6 | Campaign Page | Create campaign list + create page | Ahmed | Medium | T043, T038 | 8 | Pending
T047 | Sprint 6 | Generate Form Page | Create content generation form | Ahmed | Medium | T043, T039 | 6 | Pending
T048 | Sprint 6 | Settings Page | Create brand voice configuration page | Ahmed | Medium | T043, T023 | 6 | Pending
T049 | Sprint 6 | Web Docker Configuration | Configure Dockerfile for production build | Ahmed | Medium | T043 | 3 | Pending
T050 | Sprint 7 | Unit Tests - AI Layer | Create tests for agents and services | Shared | High | T009-T016 | 12 | Pending
T051 | Sprint 7 | Unit Tests - API Layer | Create tests for all endpoints | Shared | High | T017-T026 | 12 | Pending
T052 | Sprint 7 | Integration Tests | Create end-to-end flow tests | Shared | High | T050, T051 | 8 | Pending
T053 | Sprint 7 | CI Pipeline Setup | Create GitHub Actions workflow for lint + test | Ahmed | High | T050, T051 | 4 | Pending
T054 | Sprint 7 | Documentation Update | Update README.md, CLAUDE.md with final specs | Both | Medium | T001-T049 | 6 | Pending
T055 | Sprint 7 | Deployment Testing | Test full Docker Compose stack deployment | Ahmed | High | T002, T042, T049 | 6 | Pending
T056 | Sprint 7 | Pilot SME Onboarding | Onboard 3-5 Egyptian SMEs for pilot testing | Both | High | T055 | 8 | Pending

## Owner Summary
Owner Summary - Workload Distribution
Owner | Total Tasks | Total Hours | Primary Focus Areas
Ahmed | 32 | 177 | Orchestration, Bot, Web UI, API Auth, Content Agent, Publish
Yomna | 16 | 96 | RAG System, Chatbot Agent, Embeddings, Vector Store, Brand Memory
Shared | 8 | 53 | API Layer, MongoDB, Testing, Error Handling, Schemas

## Open Questions
Open Questions - Decision Required
Question | Needed By | Owner | Details | Status
LLM provider selection | Before first scan | Ahmed | Which model is best for Arabic dialect? Currently Gemini - should we test Mistral? | Open
Telegram vs Web priority | Before frontend build | Both | Should we focus 100% on Telegram for v1, or split effort? | Open
Brand voice collection | Before pilot | Both | How do we collect brand voice from pilot SMEs? Survey? Interview? | Open
Pilot customer recruitment | Before Phase A ends | Both | How do we find 3-5 Egyptian SMEs for pilot? | Open
Pricing for Phase B | Before v2 | Both | Is 3,000/12,000/40,000 EGP the right tier structure? | Open
Arabic dialect tuning | Before v2 | Ahmed | Should we fine-tune a model or rely on prompt engineering? | Open